## Slide 1: Change Management
What · Why · How
Testing & Quality Academy · Senior Track · Area B · Chapter B6
IT Quality · Ahmed Saleh
Notes: Welcome. Today we place Change Management inside our TMMi journey first, then answer three questions: what it is, why we need it, and how we do it at NCPD, based on the NCPD Change Management Process document.

## Slide 2: Agenda
01
Where we are
TMMi Levels 2 & 3 and our Testing & Quality framework
02
WHAT
What change management is, what a change is, types of change
03
WHY
What goes wrong without it and what we gain with it
04
HOW
Roles, the CAB, the 8-step CR process, emergency changes, the IT CR form
Notes: Four parts. Part 1 gives context: TMMi levels 2 and 3 and our Testing & Quality framework. Parts 2-4 follow the What-Why-How questions. We finish with questions and discussion.

## Slide 3: Where we are
TMMi Levels 2 & 3 and our Testing & Quality framework
Notes: Before talking about change management, let's see where it sits in the bigger picture: the TMMi model we are working towards and the framework we use in the Academy.

## Slide 4: TMMi: five maturity levels
Level 1
Initial
Testing is ad hoc and depends on individuals
Level 2
Managed
Testing is a managed process on every project
Level 3
Defined
One standard test process for the organisation, integrated in the lifecycle
Level 4
Measured
Testing is measured and quality is evaluated quantitatively
Level 5
Optimization
Defect prevention, quality control and continuous improvement
Our focus now: Level 2 → Level 3
Notes: TMMi has five maturity levels. Level 1 is initial: testing is chaotic and depends on individuals. Level 2, Managed, makes testing a disciplined process on each project. Level 3, Defined, standardises that process for the whole organisation and integrates it into the development lifecycle. Levels 4 and 5 are about measurement and optimisation. Our target now is Levels 2 and 3.

## Slide 5: Level 2 and Level 3 process areas
Level 2 · Managed
Discipline on every project
2.1
Test Policy and Strategy
2.2
Test Planning
2.3
Test Monitoring and Control
2.4
Test Design and Execution
2.5
Test Environment
Level 3 · Defined
One standard process for the organisation
3.1
Test Organization
3.2
Test Training Program
3.3
Test Lifecycle and Integration
3.4
Non-functional Testing
3.5
Peer Reviews
Notes: Level 2 has five process areas that make each project's testing managed: policy and strategy, planning, monitoring and control, design and execution, and the test environment. Level 3 adds five more that make the process organisation-wide: a test organisation, a training programme, lifecycle integration, non-functional testing and peer reviews. Change management touches several of them, mainly 2.3, 2.4 and 3.3.

## Slide 6: Our Testing & Quality framework
AREA A
Who We Are
A1 Organization Structure & IT Relationships · A2 Test Policy
AREA B
The Rules
B3 Test Strategy · B4 Lifecycle & Integration · B5 Quality Gates · B6 Change & Configuration Mgmt (CCB & CAB)
TODAY · B6
AREA C
Preparing
C7 Test Planning & Risk Assessment · C8 Tool Setup · C9 Test Environment & Test Data (optional)
AREA D
Doing the Work
D10 Grooming & Estimation · D11 Test Design & Execution · D12 Defect Management
AREA E
Control
E13 Monitoring & Control · E14 Reviews · E15 Risk · E16 KPIs & Breaches · E17 RCA · E18 CAPA · E19 Audits
AREA F
Close & Learn
F20 Test Closure & Lessons Learned
Notes: This is our framework: six areas that follow one release from start to finish. Today's topic, Change and Configuration Management, is chapter B6 in Area B, The Rules. It comes after Quality Gates because the CAB approves changes to production, which depends on the release gate.

## Slide 7: Where change management meets TMMi
TMMi practice | What it means for change management
2.4 SP1.4 · Maintain horizontal traceability | Requirement → test → defect links show exactly what a change affects and what to retest
2.4 SP4.1 · Decide disposition in a control board | Every change request gets a recorded decision: approved, rejected or deferred
2.3 SP1.1 / SP2.3 · Monitor plan and product risks | An approved change triggers re-planning and a fresh look at product risks
GP2.6 · Manage configurations | Baselines, versions and CR records stay under control and traceable
3.3 SG2 · Integrate lifecycle models | The CAB and the Go/No-Go gate are fixed points of our standard lifecycle
Notes: Change management is not a separate TMMi process area, but several practices depend on it. Traceability tells us what a change affects. Incidents and change requests need a board decision. A change means re-planning and re-assessing risk. Configuration management keeps baselines under control. And at Level 3 the CAB becomes a fixed point in our integrated lifecycle.

## Slide 8: WHAT?
What is change management, and what counts as a change?
Notes: Part 2: What. We start with the definition used by IT Services.

## Slide 9: What is a change?
“A change is anything that transforms, alters, or modifies the operating environment or standard operating procedures or service that has the potential to affect the stability and reliability of the infrastructure or disrupt business flow.”
Purpose
Manage changes to IT Services-maintained technology in a way that minimizes risk and impact to systems, applications, databases, devices and communications.
Scope
All members of IT Services, authorized members and service owners, for changes to all IT Services-managed live IT systems or services.
Mission
IT Services manages the life cycle of all systems supporting business and technical objectives. All change control processes are set out in the procedure.
Notes: Read the definition from the NCPD document. The key words: anything that transforms, alters or modifies the operating environment, a standard operating procedure or a service, and that could affect stability, reliability or business flow. Then purpose, scope and mission as defined in the document.

## Slide 10: Why do changes happen?
Business change requests
Vendor recommended or required changes
Changes in regulations
Hardware / software upgrades & updates
Hardware or software failures
Fixing defects in systems
Infrastructure changes
Environmental changes (power, cooling, data center)
Unforeseen events
Security requirements
Periodic maintenance
…and any other event that can affect stability or business flow
Notes: Changes come from many directions, not only business requests. The document lists these eleven sources. Ask the audience which of these they have seen in the last month.

## Slide 11: Types of change at the IT CAB
Normal
Minor / routine
Low-risk changes with known, well-documented procedures. Can be done at any time.
Pre-Approval
Scheduled operation
Routine changes done frequently. Approved once by the CAB; no new approval needed each time.
New Function / Feature
New development
Deployment of new features, functionality, services or applications. Not a fix to a problem.
Emergency / Unscheduled
Immediate attention
Unscheduled outages (server crashes, client complaints…) that need attention whenever they happen.
Catastrophic
Emergency CAB
Sudden, very harmful or disastrous change. Emergency CAB decides, e.g. moving to the DR site.
Notes: These are the five change types defined for the IT CAB. Normal changes are low risk with known procedures. Pre-approved changes are frequent, scheduled operational changes that the CAB approves once. New function or feature is for deploying something new, not for fixing a problem. Emergency or unscheduled changes deal with outages. Catastrophic changes need the Emergency CAB, for example the decision to move to the DR site.

## Slide 12: Two levels of change control
Project Change Request
Software development project
Changes scope, requirements or baseline
Reviewed by Project Manager & Business Analyst
Impact analysis by Development & QA
Approved by CAB or Steering Committee
Updates project scope, plan and backlog
IT Change Request (IT CR)
Live IT systems and services
Changes production systems, infrastructure or services
Numbered CR# [Serial]-[YYYY], raised by the requester
Reviewed with the CAB owner before the IT CAB meeting
Service owner approval mandatory if their services are affected
Deployed in an agreed time slot with rollback plan
Approved & tested project change becomes an IT CR for production
Notes: In our framework we separate two decisions. Inside a software development project, a change request changes the scope or baseline; it is reviewed by the PM and BA and approved by the CAB or the Steering Committee. Before anything reaches a live system, the IT change request goes to the IT CAB. A project change usually ends up as an IT CR when it is deployed.

## Slide 13: WHY?
Why do we need change management?
Notes: Part 3: Why. Start with a question to the audience: what happened the last time a change went to production without being reviewed?

## Slide 14: Without it vs. with it
Without change management
Unplanned outages that disrupt business flow
Untested changes reaching production
Nobody knows what changed, when, or by whom
Scope, timeline and budget surprises
No way back when a change fails
Gaps in audit and compliance evidence
With change management
Risk and impact minimized for systems, applications, databases, devices and communications
Stable, reliable infrastructure and business flow
Every change justified, assessed and formally decided
Impact on scope, time and cost known before approval
Rollback plan and post go-live sanity check for every CR
CRs archived for audit and compliance
Notes: Left side: what we see when changes are not managed. Right side: what the NCPD process gives us. Every item on the right comes from the procedure: risk and impact minimised, justification, impact analysis on scope, time and cost, a formal decision, rollback plans, post go-live checks, and archived CRs for audit and compliance.

## Slide 15: Why it matters for testing
Impact analysis
Development & QA analyse impact on functionality, architecture, performance and dependencies
Regression scope
Unit, integration and regression testing are part of every change, plus UAT if required
Evidence on the CR
Test steps, results, tester and acceptance signatures are fields on the IT CR form
Post go-live check
A sanity check after deployment confirms the change worked in production
Notes: For testers, change management is where our work becomes visible. We find the impact through traceability, define the regression scope, write test steps and results on the CR form, sign the acceptance, and run the sanity check after go-live. This is also the evidence TMMi assessors and auditors look for.

## Slide 16: HOW?
Roles, the CAB, the CR process and the IT CR form
Notes: Part 4: How. This is the longest part: who is involved, how the CAB works, the eight steps of the change request process, emergency changes and the IT CR form.

## Slide 17: Roles and responsibilities
Technical Change Advisory Board
Ensures changes follow the Change Management Procedure. Reviews the procedure to keep it up to date and relevant. Defines which service-owner approvals are required.
IT Services Staff (technical role)
Follow the prescribed change management processes and procedures.
IT Services Executive
Overall responsibility for the change management policy and its processes. Ensures that all staff follow it. At least one member sits on the CAB.
Service Owners
Approval is mandatory when a change affects their related services.
Everyone in IT Services has a potential role and responsibility in change management.
Notes: Everyone in IT Services has a role in change management. The Technical CAB guards the procedure and keeps it current. Technical staff follow it. The IT Services Executive owns the policy and makes sure everyone follows it. Service owners must approve changes that affect their services.

## Slide 18: The Change Advisory Board (CAB)
Purpose
Review change requests and determine whether they should be made
May require a change to be altered before it is accepted for implementation
Service owner approval is mandatory when a change affects related services
Required service-owner approvals are defined by the Technical CAB, based on CAB discussion
Changes are reviewed with the CAB owner before the IT CAB meeting
7 + 1
Members: the seven sections of the service catalogue + at least one IT Services Executive
Monthly
Regular IT CAB meeting for all required IT CR deployments
Emergency CAB
For catastrophic changes, e.g. the decision to move to the DR site
Notes: The CAB reviews change requests and decides whether they should be made; it can also ask for a change to be altered before it is accepted. Membership follows the seven sections of the service catalogue plus at least one IT Services Executive. Note for the presenter: section 4 of the document says the IT CAB meets monthly, while the appendix mentions a weekly IT CAB meeting. Confirm the current cadence before presenting.

## Slide 19: The change request process: 8 steps
1
Submission
Output
CR form / ticket
2
Review & categorize
Output
Category & owners
3
Impact analysis
Output
Impact report
4
Approval & decision
Output
Recorded decision
5
Planning
Output
Updated plan & backlog
6
Build & test
Output
Tested change
7
Deploy & release
Output
Validated release
8
Docs & closure
Output
Archived CR & lessons
Highlighted: the steps where QA is directly involved
Notes: In a software development project, every change request follows these eight steps. Each step has an owner and a clear output. The next four slides go through them two at a time.

## Slide 20: Steps 1–2 · Submit, review and categorize
1
Submission of change request
Who: Stakeholders (clients, PMs, developers, QA…)
How: formal Change Request Form or issue tracking tool
Change description
Reason: business or technical justification
Impact on scope, timeline and budget
Priority and urgency level
2
Initial review & categorization
Who: Project Manager and Business Analyst
Minor
e.g. UI modification
Major
e.g. new feature
Critical
e.g. security update
Validate the necessity of the change
Assign responsible team members
Notes: Step 1: any stakeholder can submit a change request, using the formal CR form or the issue tracking tool, with description, justification, impact and priority. Step 2: the PM and BA validate the need, categorize it as minor, major or critical, and assign the responsible people.

## Slide 21: Steps 3–4 · Analyse impact and decide
3
Impact analysis
Who: Development & QA teams
Impact on functionality, architecture and performance
Feasibility of implementation
Dependencies with other components
Effect on project timeline and cost
Output: a detailed impact report
4
Approval & decision-making
Who: Change Advisory Board or Steering Committee
Approved
→ Proceed with implementation
Rejected
→ Provide justification
Deferred
→ Reassess at a later stage
Documentation: formal approval and update of project scope
Notes: Step 3 is where QA comes in: together with development we analyse the impact on functionality, architecture and performance, feasibility, dependencies, and timeline and cost. The output is a detailed impact report. Step 4: the CAB or Steering Committee decides. Approved changes proceed; rejected ones get a justification; deferred ones are reassessed later. The decision and the updated scope are documented.

## Slide 22: Steps 5–6 · Plan, build and test
5
Implementation planning
Who: Development Team & Project Manager
Create or update project plans and the sprint backlog
Allocate resources
Define the testing and deployment strategy
Communicate timelines to stakeholders
6
Development & testing
Who: Development & QA
Implement changes following development best practices
Unit testing
Integration testing
Regression testing
User Acceptance Testing (UAT) if required
Notes: Step 5: the development team and PM update the plan and sprint backlog, allocate resources, define the testing and deployment strategy and communicate the timeline. Step 6: the change is built following development best practices and tested with unit, integration and regression testing, plus UAT where needed.

## Slide 23: Steps 7–8 · Release and close
7
Deployment & release
Who: Deployment team
Deploy changes to production / staging
Perform post-deployment validation
Communicate updates to stakeholders
8
Documentation & closure
Who: Project team
Update system documentation
Capture lessons learned for future improvements
Archive the CR for audit and compliance
Notes: Step 7: deploy to staging or production, validate after deployment and tell stakeholders. Step 8: update the documentation, capture lessons learned, and archive the CR for audit and compliance. This links directly to our Close & Learn area.

## Slide 24: Emergency and unscheduled changes
Critical event
Outage, server crash or client complaint that must be rushed through
Consider consequences
Each situation is different: assess the possible consequences first
Get sufficient approval
Discuss with the relevant service manager or section head
Log the approval
Record who it was discussed with and how it was approved
Catastrophic change → Emergency CAB
A sudden, very harmful or disastrous event needs an immediate Emergency CAB decision, for example the decision to switch to the DR site. Urgency changes the speed of approval, never the need for it.
Notes: Sometimes events are critical and must be rushed through. Each situation is different, so think about the possible consequences. Approval is still needed, but it can be a discussion with the relevant service manager or section head, as long as you log who it was discussed with and how it was approved. For catastrophic events, the Emergency CAB takes the decision, for example moving to the DR site.

## Slide 25: Raising an IT change request
Fill in the IT CR template
Requester completes the IT Technical Change Request
Email to get a CR number
Sent to the CAB to receive the next IT CR number
Name the file
[CR# xx-YYYY] [CR title].doc
Review with CAB owner
Before the IT CAB meeting
IT CAB decision
Changes going to production
Serial format
CR# [Serial] + [YYYY]
Change name
A brief description of about five words, in plain language and without technical jargon.
Notes: This is how an IT CR is raised. The requester fills in the IT CR template and emails it to get the next CR number from the CAB. The file is named with the CR number and title. The CR is reviewed with the CAB owner before the IT CAB meeting, which decides on changes going to production.

## Slide 26: Anatomy of the IT CR form
1 · Identification
Issuing, acceptance and deployment date/time
Change type and reason (business, security, project, vendor update, defect/testing, development)
Owner, requester, priority (P1 / P2 / P3), status
Initial source (business request, ticket, vendor ticket)
2 · The change
System group / project and system
Plain-language change description
Pre-change steps, change steps, post-change steps
Current setup and change actions (by whom)
3 · Testing & acceptance
Test steps (test cases) and who tests
Test result: successful, failed or partial
Tester signature and date
Acceptance test name, signature and date
4 · Risk & deployment
Impact analysis: risk and affected services or modules
Rollback plan if the change fails
Affected services and user communication
Deployment plan, time slot, post go-live sanity check
Notes: The IT CR form has four groups of fields. Identification: dates, type, reason, owner, requester, priority, status and source. The change itself: system, description and the steps before, during and after. Testing and acceptance: test steps, results and signatures. Risk and deployment: impact analysis, rollback plan, affected services, deployment plan, time slot and the post go-live sanity check.

## Slide 27: Best practices
Version control
Use version control to track every change
Central tracking
Maintain a centralized tracking system, e.g. Azure DevOps
Escalation matrix
Define a clear escalation matrix
Communication
Keep regular communication with stakeholders
Change freeze
Establish a change freeze policy near project deadlines
Notes: Five best practices from the procedure. Version control for every change. One central tracking system, which for us is Azure DevOps. A clear escalation matrix. Regular communication with stakeholders. And a change freeze policy close to project deadlines.

## Slide 28: Summary: What, Why, How
WHAT
A change: anything that can affect stability, reliability or business flow
11 sources of change
5 types: normal, pre-approval, new feature, emergency, catastrophic
WHY
Minimize risk and impact on live systems
Every change justified, assessed and decided
Rollback plans and a full audit trail
HOW
Clear roles and a CAB with service-owner approval
8-step CR process, from submission to closure
Emergency path and the IT CR form
Notes: Three take-aways. What: a change is anything that can affect stability, reliability or business flow, and there are five types. Why: to minimise risk and impact and to have a decision and an audit trail for every change. How: roles and the CAB, the eight-step CR process, the emergency path and the IT CR form.

## Slide 29: Questions?
Let's discuss
Which recent change would have gone better with a CR?
Where does QA join the process today, and where should it?
What would you add to the IT CR form?
Notes: Open the floor. Use the three discussion prompts if the room is quiet. Next chapter in the Academy: C7 Test Planning & Risk Assessment.